Instruction Sheet for the Candidate

| Qualification | National Diploma in Civil Technology Level-5 (P-1) (Construction Project Planning & Management) |
| --- | --- |
| Purpose of Assessment | Summative Assessment |
| Candidate Details | Name_______________________________________________________ Registration Number_________________________________________________ |
| Guidance for Candidate | To meet this standard, you are required to complete the following within 05 Hrs. time frame (for practical demonstration & assessment): - Produce documents for Admin approval and Technical Sanction. - Develop Construction project plan. - Implement quality assurance processes - Perform Activities Scheduling in Primavera P6 - Perform Resources Costing &Planning in Primavera P6 |
| Time: 05 Hrs | During a practical assessment, under observation by an assessor, you are required to: - Produce documents for Admin approval and Technical Sanction for 3 rooms of a primary school. - Develop Construction project plan for primary school building. - Conduct the supervision of primary for the purpose of quality assurances - Perform Activities Scheduling in Primavera P6 for approach road of primary school. - Perform road Project Resources Costing &Planning for approach road in Primavera P6 |
| Minimum Evidence Required | - Prepare rough cost estimate. - Get Administrative approval of project. - Prepare Detailed estimate. - Get technical sanction from the authority. - Draft construction and system feasibility- resources for project. - Decide the feasibility and prepare feasibility report of project. - Collect data from estimate of construction project. - Identify pre-construction tasks. - Specify the individual activities. - Determine the sequence of those activities. - Draw a network diagram and decide critical path including crashing. - Conduct inspections of quality processes and quality control results to determine compliance of quality standards to overall quality objectives - Maintain a quality management system to enable effective recording and communication of quality issues and outcomes to a higher project authority and stakeholders - Enter Project ID and Project Name in P6 for approach road project. - Enter Planned Start Date for the project and target deadline in ‘Must Finish by’ - Select the ‘Responsible Manager’ - Select ‘Assignment rate Type’ - Check ‘no do not run project architecture’ - Open Projects Screen and click on the newly created project - Open ‘Notebook’ tab in the opened ‘Project Detail’ window  ‘Add’  Select the type of note to be added - Open ‘Dates’ tab  Add relevant dates - Click ‘WBS’ tab on the Directory Bar on the left to open WBS Window - Create a detailed WBS along with assigning ‘Code’ and ‘Name’ to the newly added WBS Element - Add activities along with details like duration & parameters for all levels of WBS. - Assign resources to activities and create relevant relationships- the ‘Predecessors’ and ‘Successors’. - Change the activity relationship from FS to either SS, or SF or FF, as required. - Add all the relevant parameters in the ‘Schedule’ pop-up window,  Click ‘Schedule’ button on the right. - Add activity and project constraints for road project. - Create calendars for activities and assign these. - Assign non-working/working day along with changing days per week. - Create & assign Baseline and display the same. |

Self-Assessment Checklist

| Candidate Name |  |
| --- | --- |
| Registration No. |  |
| Qualification | National Diploma in Civil Technology Level-5 (P-1) (Construction Project Planning & Management) Summative Assessment |
| Purpose of Assessment | Summative Assessment |
| Assessment Task | - Produce documents for Admin approval and Technical Sanction for 3 rooms of a primary school. - Develop Construction project plan for primary school building. - Conduct the supervision of primary for the purpose of quality assurances - Perform Activities Scheduling in Primavera P6 for approach road of primary school. - Perform road Project Resources Costing &Planning for approach road in Primavera P6 |

I can……………….

| Performance Criteria | Yes | No |
| --- | --- | --- |
| - Prepare rough cost estimate. |  |  |
| - Get Administrative approval of project. |  |  |
| - Prepare Detailed estimate. |  |  |
| - Get technical sanction from the authority. |  |  |
| - Draft construction and system feasibility- resources for project. |  |  |
| - Decide the feasibility and prepare feasibility report of project. |  |  |
| - Collect data from estimate of construction project. |  |  |
| - Identify pre-construction tasks. |  |  |
| - Specify the individual activities. |  |  |
| - Determine the sequence of those activities. |  |  |
| - Draw a network diagram and decide critical path including crashing. |  |  |
| - Conduct inspections of quality processes and quality control results to determine compliance of quality standards to overall quality objectives |  |  |
| - Maintain a quality management system to enable effective recording and communication of quality issues and outcomes to a higher project authority and stakeholders |  |  |
| - Enter Project ID and Project Name in P6 for approach road project. |  |  |
| - Enter Planned Start Date for the project and target deadline in ‘Must Finish by’ |  |  |
| - Select the ‘Responsible Manager’ |  |  |
| - Select ‘Assignment rate Type’ |  |  |
| - Check ‘no do not run project architecture’ |  |  |
| - Open Projects Screen and click on the newly created project |  |  |
| - Open ‘Notebook’ tab in the opened ‘Project Detail’ window  ‘Add’  Select the type of note to be added |  |  |
| - Open ‘Dates’ tab  Add relevant dates |  |  |
| - Click ‘WBS’ tab on the Directory Bar on the left to open WBS Window |  |  |
| - Create a detailed WBS along with assigning ‘Code’ and ‘Name’ to the newly added WBS Element |  |  |
| - Add activities along with details like duration & parameters for all levels of WBS. |  |  |
| - Assign resources to activities and create relevant relationships- the ‘Predecessors’ and ‘Successors’. |  |  |
| - Change the activity relationship from FS to either SS, or SF or FF, as required. |  |  |
| - Add all the relevant parameters in the ‘Schedule’ pop-up window,  Click ‘Schedule’ button on the right. |  |  |
| - Add activity and project constraints for road project. |  |  |
| - Create calendars for activities and assign these. |  |  |
| - Assign non-working/working day along with changing days per week. |  |  |
| - Create & assign Baseline and display the same. |  |  |

Candidate’s Signature__________________ Assessor’s Signature__________________

Date: _______________________________

Assessors Judgment Guide

| Qualification | National Diploma in Civil Technology Level-5 (P-1) (Construction Project Planning & Management) |
| --- | --- |
| Purpose of Assessment | Summative Assessment |
| Candidate Details | Name:______________________________________________________________ Registration Number: ________________________ Signature: _________________ |
| Assessment Outcome | COMPETENT NOT YET COMPETENT Name of the Assessor________________________________________________ Assessor’s code:___________________ Signature:________________________ |

| Assessment Summary (to be filled by the assessor) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Method |  |  |  |  | Result |  |
| Nature of Activity | Written | Oral | Observation | Portfolio | Role Play | Competent | Not Yet Competent |
| Practical Skill Demonstration |  |  |  |  |  |  |  |
| Knowledge Assessment |  |  |  |  |  |  |  |
| Other Requirement |  |  |  |  |  |  |  |

Observation Checklist

| Assessment Task |  | - Produce documents for Admin approval and Technical Sanction for 3 rooms of a primary school. - Develop Construction project plan for primary school building. - Conduct the supervision of primary for the purpose of quality assurances - Perform Activities Scheduling in Primavera P6 for approach road of primary school. - Perform road Project Resources Costing &Planning for approach road in Primavera P6 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| During the practical assessment, candidate demonstrated the following: |  |  |  | Yes | No | Remarks |
|  | Prepare rough cost estimate. |  |  |  |  |  |
|  | Get Administrative approval of project. |  |  |  |  |  |
|  | Prepare Detailed estimate. |  |  |  |  |  |
|  | Get technical sanction from the authority. |  |  |  |  |  |
|  | Draft construction and system feasibility- resources for project. |  |  |  |  |  |
|  | Decide the feasibility and prepare feasibility report of project. |  |  |  |  |  |
|  | Collect data from estimate of construction project. |  |  |  |  |  |
|  | Identify pre-construction tasks. |  |  |  |  |  |
|  | Specify the individual activities. |  |  |  |  |  |
|  | Determine the sequence of those activities. |  |  |  |  |  |
|  | Draw a network diagram and decide critical path including crashing. |  |  |  |  |  |
|  | Conduct inspections of quality processes and quality control results to determine compliance of quality standards to overall quality objectives |  |  |  |  |  |
|  | Maintain a quality management system to enable effective recording and communication of quality issues and outcomes to a higher project authority and stakeholders |  |  |  |  |  |
|  | Enter Project ID and Project Name in P6 for approach road project. |  |  |  |  |  |
|  | Enter Planned Start Date for the project and target deadline in ‘Must Finish by’ |  |  |  |  |  |
|  | Select the ‘Responsible Manager’ |  |  |  |  |  |
|  | Select ‘Assignment rate Type’ |  |  |  |  |  |
|  | Check ‘no do not run project architecture’ |  |  |  |  |  |
|  | Open Projects Screen and click on the newly created project |  |  |  |  |  |
|  | Open ‘Notebook’ tab in the opened ‘Project Detail’ window  ‘Add’  Select the type of note to be added |  |  |  |  |  |
|  | Open ‘Dates’ tab  Add relevant dates |  |  |  |  |  |
|  | Click ‘WBS’ tab on the Directory Bar on the left to open WBS Window |  |  |  |  |  |
|  | Create a detailed WBS along with assigning ‘Code’ and ‘Name’ to the newly added WBS Element |  |  |  |  |  |
|  | Add activities along with details like duration & parameters for all levels of WBS. |  |  |  |  |  |
|  | Assign resources to activities and create relevant relationships- the ‘Predecessors’ and ‘Successors’. |  |  |  |  |  |
|  | Change the activity relationship from FS to either SS, or SF or FF, as required. |  |  |  |  |  |
|  | Add all the relevant parameters in the ‘Schedule’ pop-up window,  Click ‘Schedule’ button on the right. |  |  |  |  |  |
|  | Add activity and project constraints for road project. |  |  |  |  |  |
|  | Create calendars for activities and assign these. |  |  |  |  |  |
|  | Assign non-working/working day along with changing days per week. |  |  |  |  |  |
|  | Create & assign Baseline and display the same. |  |  |  |  |  |
| Competent |  |  | Not Yet Competent |  |  |  |

Knowledge Assessment

| Qualification | National Diploma in Civil Technology Level-5 (P-1) (Construction Project Planning & Management) |
| --- | --- |
| Purpose of Assessment | Summative Assessment |
| Candidate Details | Name: _____________________________________________________________ Registration Number: _________________ Candidate Signature: _____________ |
| Assessment Outcome | COMPETENT NOT YET COMPETENT Name of the Assessor: __________________________ Assessor’s code: _________________ Signature of the Assessor: ______________ |

Candidate’s response is not required to be identical, but similar concepts and/or keywords must be used. Oral questioning may be used to clarify candidate understanding of topic and its application.

| Questions (Candidate confidently answered questions correctly and demonstrated understanding of the topics and their application) |  | Satisfactory | Not Satisfactory |
| --- | --- | --- | --- |
|  | State project management life cycle? |  |  |
|  | State the stages involved in construction projects? |  |  |
|  | State the importance of preliminary planning? |  |  |
|  | What is meant by Pre-feasibility study? |  |  |
|  | What is meant by sequencing of activities and scheduling? |  |  |
|  | What is meant by yield/ productivity of construction machinery? |  |  |
|  | State the main factors in selection of construction machinery? |  |  |
|  | What is the need for inspection of works? |  |  |
|  | What is the use of site order book? |  |  |
|  | State the principles of supervision? |  |  |
|  | What are the points to be considered in enforcing specifications? |  |  |
|  | State legislation in regard to occupational health and safety and environmental issues? |  |  |
|  | State the names and function of all Views in P6? |  |  |
|  | How layouts are customized in Primavera P6? |  |  |
|  | State types of Project constraints? |  |  |
|  | Define resource and enlist its types? |  |  |
|  | What is a Gantt Chart? |  |  |
|  | Define task dependent activity, resource dependent activity? |  |  |
|  | Define start milestone activity? |  |  |
|  | Define work/non-work days? |  |  |
|  | State the use of Baselines in evaluating project performance? |  |  |
|  | What is meant by project control? |  |  |
|  | What is the use of Progress Spotlight? |  |  |
|  | How timeline of the spotlight is increased/ decreased? |  |  |
|  | How actual activity start and completion dates are entered? |  |  |

Feedback to the Candidate

Candidate’s Signature__________________ Assessor’s Signature ___________________