Course / Subject Name: NQ-Civil-304 Construction Project Planning & Management

- MCQs

| Formative Assessment (Part A) | Formative Assessment (Part B) | Formative Assessment (Part C) |
| --- | --- | --- |
| LU 1-3 | LU 4-6 | LU 7-9 |
| - primary goal of the project management life cycle is - To implement all project tasks simultaneously - To ensure that the project is completed within the approved scope, schedule, and budget - To reduce the number of stakeholders involved - To minimize project risks by eliminating all potential issues - _______ phase of the project management life cycle focuses on defining project objectives and identifying project stakeholders - Planning Phase - Initiation Phase - Execution Phase - Closing Phase - In _______ phase of the project management life cycle, the project officially closed, and all contractual obligations are completed. - Execution Phase - Planning Phase - Initiation Phase - Closing Phase - ___________ is a key activity in the execution phase of the project life cycle - Establishing project objectives - Monitoring project progress and performance - Conducting post-project evaluations - Assigning resources to complete the project plan - The significance of a Work Breakdown Structure (WBS) during the planning phase of the project life cycle is - To serve a communication tool for stakeholders - To divide the project into manageable sections or tasks - To identify project risks - To track the performance of team members - Preliminary planning is essential before the start of a project, Since it_____ - It helps to complete the project faster. - It identifies potential risks and defines project scope and objectives. - It ensures that there are no costs involved in the project. - It eliminates the need for resources. - The primary purpose of the technical sanction procedure in project management is? - To approve the project budget - To get approval from stakeholders - To verify and approve the technical design and cost estimates before project execution - To evaluate the project team’s performance - The main objective of conducting a pre-feasibility study for a project? - To assess whether the project is viable from a technical, financial, and legal standpoint - To estimate the final cost of the project - To create working drawings for the project - To select the project team - First step in conducting a feasibility study is? - Analyzing financial risks - Gathering data and understanding project scope - Evaluating design alternatives - Finalizing the project report - "Dummy activity" in project scheduling is defined as? - An activity with no duration, used to show dependencies between tasks - An activity that does not require any resources - An activity that can be completed after the project is finished - An activity that adds extra time to the project schedule - "Predecessor" activity describes as? - An activity that is completed after another activity - An activity that has no other task dependent on it - An activity that must be completed before another activity can start - An activity that does not require resources - The purpose of arranging project activities in sequence is? - To allocate resources more efficiently - To establish the project’s budget - To ensure the activities are performed in the correct order and dependencies are respected - To select the right team for each task - The main purpose of defining the relationships between activities in project scheduling is? - To identify the project budget - To ensure that one activity logically follows another and to determine dependencies - To estimate the time required for each activity - To assign resources to activities - The purpose of determining the late finish time (LF) and late start time (LS) for an activity is? - To estimate the total cost of the project - To ensure that the activity is completed within the required project timeline - To identify the resources needed for each task - To define the relationships between project tasks - What is the "critical path" in project scheduling? - The sequence of tasks that require the most resources - The sequence of tasks that determines the minimum project duration, with zero float or slack time - The longest path through the project schedule - The path with the least cost Answer Key 1; B. 2; B. 3; D. 4; D. 5; B. 6; B. 7; C. 8; A. 9; B. 10; A. 11; C. 12; C. 13; B. 14; B. 15; B. | - Select the established quality management tool used to analyze the preferred mix of quality, capability, cost, and time in a project? - Gantt Chart - Pareto Analysis - Critical Path Method (CPM) - SWOT Analysis - The main purpose of reviewing agreements related to quality criteria in a project is? - To assess the financial implications of quality standards - To ensure all stakeholders have a clear understanding and agreement on quality expectations - To identify the resources required for project completion - To determine the project timeline - To measure and document results of project activities is important, beacuse? - It ensures compliance with financial constraints - It determines the efficiency of resource usage - It verifies the quality standards are being met and document performance for future reference - It predicts the final project completion date - The role of a quality management system (QMS) in a project is? - To record financial transactions - To facilitate effective documentation, tracking, and addressing of quality issues and outcomes - To select the project team - To monitor the weather conditions at the project site - The effectiveness of quality management processes and procedures is determined by? - Comparing project outcomes against pre-defined performance criteria and quality standards - Reviewing the project schedule and ensuring timely completion - Assessing the project's financial health - Evaluating stakeholder satisfaction - Workforce and machinery enhancement can directly impact project quality? - By increasing project costs without improving quality - By ensuring sufficient resources to maintain high quality standards and meet deadlines - By decreasing productivity and quality - By delaying the project timeline due to equipment breakdowns - Purpose of the Layout Options Bar in Primavera P6 is? - To navigate through different software versions - To configure display settings for different views and layouts within the software - To access the project cost data - To load project templates - Columns can be added to the layout in Primavera P6 by? - By right-clicking the project name - By clicking on the "Activities" tab - By opening the "Reports" menu - By selecting "Columns" from the "View" menu and then choosing the required columns - The first step to display the Gantt chart and select a WBS in Primavera P6 is? - Open the "Resources" tab and click on "WBS" - Open the "Project" menu and select "WBS" - Open the "Activities" tab and select the Gantt chart view, then choose the WBS from the left-hand side - Use the "Schedule" tab to view the Gantt chart - In Primavera P6, how can you capture a screenshot of your screen or part of it? - By pressing "Ctrl + Print Screen" - By using the Snip & Sketch tool in Windows or a third-party screen capture tool - By selecting "Export" from the "File" menu - By using the "Snapshot" option under the "Tools" menu - Select appropriate action to create a detailed WBS and add an activity in Primavera P6? - Right-click the WBS element and select "Create Activity" - Select "Add" in the WBS window, then input activity details under each WBS element - Go to the "Resources" tab to add activities - Open the "Project" menu and select "New Activity" - Select the process for entering the expected activity duration in Primavera P6? - In the "Duration" column under the Gantt chart - In the "Start Date" column - In the "WBS" window next to each activity - In the "Original Duration" column in the Activities window - Activities can be added to different WBS levels in Primavera P6 by? - By selecting the WBS element and clicking "Add Activity" in the WBS window - By selecting the activity, right-clicking, and choosing "Move to WBS Level" - By selecting "Project" and then clicking "New WBS Level" - Activities are automatically added to the first WBS level, no manual entry is required - Relationships between the activities in the Gantt chart view can be configured by? - By right-clicking on an activity and selecting "Configure Relationships" - By dragging the activity bars in the Gantt chart to connect tasks - By selecting an activity and then clicking the "Relationships" tab to define predecessor and successor - By adding resource dependencies to the activities - Relationship arrows in the Gantt chart represents? - The total duration of the project - The link between activities showing the flow of project tasks from predecessor to successor - The resources assigned to each activity - The cost distribution between activities - An activity can be predecessed in Primavera P6 by? - By entering the task's ID in the "Predecessor" column - By dragging the activity in the Gantt chart to another activity - By selecting an activity and clicking the "Predecessor" button to choose the preceding task - Predecessors are automatically generated based on task dependencies Answer Key 1; B. 2; B. 3; C. 4; B. 5; A. 6; B. 7; B. 8; D. 9; C. 10; B. 11; B. 12; D. 13; A. 14; C. 15; B. 16; C. | - In Primavera P6, which of the following is used to assign resources to activities? - A) Resource Assignments - B) Activity Codes - C) Work Breakdown Structure (WBS) - D) Resource Calendars - Which of the following best defines the "Cost Account" in Primavera P6? - A) A unique identifier for a resource - B) A hierarchical structure to manage costs - C) A code used to categorize tasks - D) A unique identifier for an activity 3. In Primavera P6, what is the purpose of the "Resource Histogram"? - A) To display the resource allocation over time - B) To show the project’s critical path - C) To identify resource conflicts - D) To calculate earned value 4. What does the "Budgeted Cost of Work Scheduled" (BCWS) represent in Primavera P6? - A) The cost of work performed to date - B) The cost of work that is planned to be completed by a specific date - C) The total cost of all resources on the project - D) The actual cost incurred for activities 5. Which of the following steps is necessary to apply resource leveling in Primavera P6? - A) Create a baseline - B) Adjust the activity duration - C) Apply constraints to tasks - D) Automatically reschedule the project - In Primavera P6, what is the primary purpose of identifying "lags" in a project schedule? - A) To calculate the project’s earned value - B) To identify delays in the project timeline - C) To allocate additional resources to activities - D) To assess the overall project budget 7. Which of the following best describes a "lag" in Primavera P6? - A) The time delay between the completion of one activity and the start of another - B) The total duration of a project - C) A specific task that cannot be completed within the project duration - D) The difference between the planned start and finish dates of an activity 8. In Primavera P6, how can you identify a lag in the project schedule? - A) By viewing the "Critical Path" and identifying any delays - B) By reviewing the "Relationship" tab of activities and looking for negative lags - C) By analyzing the "Resource Usage" profile - D) By generating a "Cost Performance Index" report 9. When monitoring a project in Primavera P6, what action should be taken if a lag is identified in the schedule? - A) Increase the duration of all activities - B) Reassign resources to the delayed tasks - C) Adjust the schedule to remove the lag or mitigate its impact - D) Change the project’s baseline to reflect the new delays 10. Which of the following is an example of a "negative lag" in Primavera P6? - A) A delay between finishing one activity and starting the next - B) A lag between the start of one activity and the start of another - C) A situation where an activity must start before the preceding activity ends - D) A delay between resource allocation and activity start 11. What is the primary goal of identifying project risks during the early stages of a project? - A) To assess the project’s quality control measures - B) To establish a project baseline - C) To mitigate or eliminate potential threats to the project's success - D) To allocate resources more effectively 12. Which of the following is an example of a "schedule risk" in a project life cycle? - A) Increased material costs due to price fluctuation - B) A key team member becoming unavailable during critical project phases - C) Failure to comply with regulatory requirements - D) A change in project scope during execution 13. How do project risks typically affect the project life cycle? - A) They improve team communication and collaboration - B) They cause delays, increase costs, or compromise project quality - C) They have no impact on the project’s timeline or budget - D) They enhance the project's stakeholder engagement 14. Which risk management process is used to determine the probability and impact of a risk event in a project? - A) Risk Identification - B) Risk Analysis - C) Risk Response Planning - D) Risk Monitoring and Controlling 15. What is the potential consequence of not identifying and managing risks during the planning phase of a project? - A) The project will be completed ahead of schedule - B) The project will have no cost overruns - C) Unforeseen issues may arise during execution, leading to delays and increased costs - D) The project will receive high-quality stakeholder feedback - Answer Keys 1; A. 2; B. 3; A. 4; B. 5; D. 6; B. 7; A. 8; B. 9; C. 10; C. 11; C. 12; B. 13; B. 14; B. 15; C. |

- Limited Response Questions

| Formative Assessment (Part A) | Formative Assessment (Part B) | Formative Assessment (Part C) |
| --- | --- | --- |
| - Define Initiation Phase. - Breif the importance of relationship between activities - What is organogram? - Enlist the phases of project management life cycle. - Describe the reltionship between time and cost. - State the importance of preliminary planning. - Define dummy activity. - Define predecessor. - Describe successor. - What is gantt chart? - Define the purpose of bar chart. - Define critical path. | - Breif the importance of quality management. - Enlist the quality management technicques. - Enlist three responsibilities of project manager - Enlist three responsibilities of site engineer - Define the use of site order book. - Define closing phase of project life cycle. - Define monitoring and controlling phase. - Differentiate between actual and budgeted cost. - Define work break down structure (WBS). - Define milestone. - Define total float. - State free float. - Enlist the relationship types between activities. | - Define purpose of assigning resources to activities in Primavera P6. - Describe the concept of "Resource Leveling" in Primavera P6. - Role of the "Earned Value Management" (EVM) in Primavera P6. - Describe how resource calendars are used in Primavera P6. - "Lag" in Primavera P6, and importants during a construction project - Identify a lag between activities in Primavera P6. - Steps taken in Primavera P6 if you identify an excessive lag between two activities. - Impact of a "negative lag" in Primavera P6, and its affects. - Identify risks during the early stages of the project life cycle. 11. Consequences of ignoring risks during the execution phase of a project. 12. Impact of risk analysis in the decision-making process during a project's life cycle. 13. Role of risk management in ensuring a project's successful completion. |

- Assessment Tasks

| Formative Assessment (Part A) | Formative Assessment (Part B) | Formative Assessment (Part C) |
| --- | --- | --- |
| - Draft project management life cycle of a road project Performance Criteria; - Carryout Preliminary survey for a road project. - Perform Detailed Survey & Design Project features. - Prepare project organogram - Identify project milestones and objectives - Develop project logs - Prepare cost estimate and drawings | - Prepare construction schedule for road project Performance Criteria; - Load Primavera P6 Software and prepare interface for a road project. - Create WBS. - Create Activities, assign durations. - Develoip relationship between activities. - Assign milestones. - Prepare a Gantt chart. - Identify critical activities. - Claculate free float and total float. | Prepare Risk Breakdown Structure. Performance Criteria; - Develop a detailed flowchart outlining each stage from project initiation - highlighting key milestones and deliverables. - Construct a hierarchical diagram - identified risks into major risk categories and sub-categories - providing a structured view of potential project risks |