Course / Subject Name NQ-Civil-304 Construction Project Planning & Management

Assessment Task 01 (Summative Assessment)

Develop project management life cycle for a Building Project

- Carryout preliminary survey.

- Perform detailed survey & design project features.

- Prepare project organogram

- Identify project milestones and objectives

- Develop project logs

- Prepare cost estimate and drawings

- Draft initiation phase

- Draft planning phase

- Draft execution phase

- Draft monitoring & controlling phase

- Draft closing phase

Assessment Task 02 (Summative Assessment)

Prepare construction schedule in Primavera P6 for a building project

- Load Primavera P6 Software and prepare interface for a building project.

- Create enterprise.

- Set calender.

- Create WBS.

- Create Activities, assign durations.

- Develoip relationship between activities.

- Assign milestones.

- Prepare a gantt chart.

- Identify critical activities.

- Claculate free float and total float.

Assessment Task 03 (Summative Assessment)

Identify Risk in the Project and how the consequences can be avaoided.

- Plan to identify risks in each phase of project

- Develop a detailed flowchart outlining each stage from project initiation to completion

- Highlighting key milestones and deliverables.

- Construct a hierarchical diagram

- Categorizing identified risks into major risk categories and sub-categories

- Providing a structured view of potential project risks.